## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Status Report
| Table 1 | Status Report
Sheet1
| Table 1 | Sheet1

## Status Report
Project Name | Rook |  | Date |  | 2022-02-05 | Project Manager |  | Joseph Corey
Project Summary (including redirection) |  |  |  | Key Tasks |  | Progress | Status |  | Finish
Rook is a card game, and is the basis to Skull King and other similar games. This project is to make an online game of Rook that can be multiplayer. | [5 empty] | 90% | On Track
[6 empty] | 70% | Possible Delays
[6 empty] | 43% | Delayed
[6 empty] | 26% | Complete
[6 empty] | 78% | On Track
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
[6 empty] | 0% | Future Task
Tasks Completed |  |  | Tasks Delayed |  |  | Tasks Planned
Creation of requirements document, plan for each of the demos
Team Members -- Billable Hours |  |  | Key Project Risks and Issues
Name | Role/Task | Hours | Type | Risks or Issue Description
Joseph Corey | Project Manager/Quint. QA | 2 | Risk
Benjamin Jacobs | Chief Architect | 1
Avery Bates | Wiki Wizard/Dream Dev | 2.5
Cameron Dodds | Dream Developer | 1 | Issue | .
Lydia Day | Graphics Guru | 5
Grant Windsor | Unreplaceable UX | 3.5
Total |  | 15

## Sheet1
On Track | Issue
Possible Delays | Risk
Delayed
Complete
Future Task